## Decomm
Clusters | Customers | Stage | Prod | Start Date | End Date | ChangeCase
AMS-18300148-STAGE-UUW-C0068 | MISYS Prod and Stage | Completed | Already Decommissioned | 17/04/19 | 18/04/19 | IS-01349431
AMS-18300148-STAGE-UUW-C0068 | RABOBANK Prod and Stage | Completed | Completed |  |  | IS-02773353
|  |  |  | 2019-04-15 | 2019-04-15
DSM-18300148-STAGE-UUW-C0132 | EQUINIX Prod and Stage | Completed | Completed | 2019-04-09 | 2019-04-09 | IS-02723214
DSM-18300148-STAGE-UUW-C0132 | SEMINOLEGAMING Prod and Stage | Completed | Completed | 2019-04-05 | 2019-04-10 | IS-02791299
DSM-18300148-STAGE-UUW-C0142 | CHEVRON_PROD and Stage | Completed | Completed | 24/04/19 | 25/04/19 | IS-02791299
CMH-18300148-PROD-UUW-C0111
DSM-18300148-STAGE-UUW-C0133 | GROTE_STAGE | Completed | Completed | 29/04/19 | 30/4/2019 | IS-02766134
DSM-18300148-STAGE-UUW-C0133 | BAXTER_STAGE | Yet to Start | Yet to Start | 13/05/19 | 14/05/19 | IS-02773409
DSM-18300148-STAGE-UUW-C0136 | KORE_STAGE | Yet to Start | Yet to Start | 20/05/19 | 21/05/19 | IS-02766816
DSM-18300148-STAGE-UUW-C0136 | SIOS_STAGE | Yet to Start | Yet to Start | 27/05/19 | 28/05/19 | IS-02833653
DSM-18300148-STAGE-UUW-C0142 | LIBERTYMUTUAL_STAGE | Yet to Start | Yet to Start
DSM-18300148-STAGE-UUW-C0142 | WIPROLEARNING_STAGE | Yet to Start | Yet to Start
DSM-18300148-STAGE-UUW-C0142 | CIPLABIOTEC_STAGE | Yet to Start | Yet to Start
DSM-18300148-STAGE-UUW-C0142 | PACIFICORP_STAGE | Yet to Start | Yet to Start
DSM-18300148-STAGE-UUW-C0142 | MAHINDRA_STAGE | Yet to Start | Yet to Start
DSM-18300148-STAGE-UUW-C0142 | MURUGAPPA_STAGE | Yet to Start | Yet to Start
DSM-18300148-STAGE-UUW-C0144 | SKANDIA_STAGE | Yet to Start | Yet to Start
DSM-18300148-STAGE-UUW-C0144 | WAKEMED_STAGE | Yet to Start | Yet to Start
DSM-18300148-STAGE-UUW-C0133 | WATANMAL_STAGE | Yet to Start | Yet to Start
DSM-18300148-STAGE-UUW-C0132 | CITRIX_STAGE | Yet to Start | Yet to Start |  |  | IS-02041477
CMH-18300148-PROD-UUW-C0111 | CBIDEVELOPMENT_PROD | Completed | Completed | 2019-06-05 | 2019-06-05 | IS-02719563

## Automation
TestCases | Start Date | End Date | Status
Test1) LM sitemap working |  |  | Completed
a. Click on any links in the LM pages ( Admin icon -> Product administration -> Learning -> administrator dashboard or any other link )
Test 2) LM upload working | 01/05/19 | 03/05/19 | InProgress
a. Upload any simple .txt document (Admin icon -> Product administration -> Learning -> Learning Activities -> Click on File Upload -> Browse, select the .txt file -> click on Upload files -> click on Next -> Provide Activity name -> click on Next -> click on upload -> goto Previously uploaded link on the same screen -> click on drop down – View items in staging -> File should be shown with status “In Staging”
Test 3) Verify Search | 2019-08-05 | 2019-10-05 | Yet to Start
a. Click on Search icon on the top right -> search for admin ( you should see all users with admin name ) -> search for activities ( you should see all Navigation items with this name ), if it is TM search for TM related navigation items |  |  | Yet to Start
Test 4) Core Sitemap | 15/5/19 | 17/5/19
a. Create a User ( Admin icon -> Common objects -> Users -> All users -> Create user -> try to create a sample user |  |  | Yet to Start
Test 5) Core Data Import | 22/5/19 | 24/5/19
a. Run the Default Data Import Job (Admin icon -> Common objects -> Data -> Data Import) by selecting the sample files
b. Run the Training Migration Job (Admin icon -> Common objects -> Data -> Data Import) by selecting the sample files |  |  | Yet to Start
Test 6) Reporting | 29/5/19 | 31/5/19
a. LM report test - Click on Team icon in the middle ( Reporting -> Advanced reporting -> client# -> reports -> Audience -> Audience User Association report |  |  | Yet to Start
b. TM report test - Click on Team icon in the middle ( Reporting -> Advanced reporting -> client# -> reports -> TMadmin -> Batch job status |  |  | Yet to Start
Test 7) TM Batch jobs | 2019-05-06 | 2019-08-06
a. Check if any of the Batch jobs is working ( Admin icon -> Setup -> Talent -> System -> Batch Jobs -> Batch processes -> select on ‘S’ -> goto the end for “System – Upgrade Post Process -> drop down -> select Run -> Yes -> U will see change in the Last processed time stamp -> drop down -> click on View Log -> U will the timestamp that it was run. If the job was not run or seen here, goto Running jobs, it would be listed in queue. |  |  | Yet to Start

## Auto_Tc's
Test_Case | TimeTaken | Execution | Status
LM_Setup_CoValidations | 00:03:51 | Execution complete. | Pass
LM_NewActivity_Wizard_for_xAPI | 0:03 | Execution complete. | Fail